## Project Planner
Ebersoft Gantt Chart | [19 empty] | Each period is representative of 5 days starting on February 27th, 2017
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Search Function FE | 1 | 3 | 1 | 6 | 78%
Display List FE | 1 | 3 | 1 | 9 | 70% | bar: PERIODS 2
Display Item FE | 1 | 5 | 1 | 8 | 60% | bar: PERIODS 2
Dashboard 1 FE | 3 | 5 | 2 | 6 | 60%
Dashboard 2 FE | 3 | 5 | 3 | 8 | 60%
Dashboard 3 FE | 3 | 5 | 3 | 8 | 60%
Dashboard 4 FE | 3 | 5 | 3 | 8 | 60%
Dashboard 5 FE | 3 | 5 | 3 | 9 | 60%
Search Function Java | 1 | 5 | 1 | 5 | 100%
Search Function Database | 1 | 5 | 1 | 6 | 100%
View Item Info Java | 3 | 5 | 4 | 9 | 100%
View Item Info Database | 3 | 5 | 3 | 5 | 53%
Google Charts Info | 1 | 3 | 1 | 8 | 70%
MySQL Database | 1 | 3 | 1 | 8 | 30%
Save Item | 3 | 7 | 3 | 7 | 67%
Prototype | 1 | 2 | 1 | 2 | 100%
| 0 | 0 |  |  | 0%
| 0 | 0 |  |  | 0%